## Slide 1
Erasmus+ Capacity Building in Higher Education
WP3: Curriculum Development Twinning
Session 1: Overview & Twinning Model
WP3 Kick-off Meeting
GREEN FINANCE Project
August 2026 | Virtual Meeting

## Slide 2
Slide 2 of 10
WP3 in GREEN FINANCE
Curriculum Development Twinning
Project Work Package Structure
WP1
Project Management
M1-M36
Coordination
WP2
Landscape Analysis
M1-M12
Research
WP3
Curriculum Development
M8-M22
Development
WP4
Piloting & Evaluation
M19-M30
Implementation
WP5
Dissemination
M1-M36
Outreach
WP3 Focus: Develop and deliver a twinning program where EU partners train Asian staff to create and implement the Green Finance microcredential curriculum.
GREEN FINANCE | WP3 Kick-off

## Slide 3
Slide 3 of 10
WP3 Objectives
Curriculum Development & Capacity Building
1
Develop Training Materials
Create comprehensive teaching resources for 5-module Green Finance curriculum
2
Build Capacity
Train 24 Asian staff (4 per HEI) in curriculum development and delivery
3
Implement Twinning
EU-Asian partnership model for knowledge transfer
4
Deliver Pilot Curriculum
Support Asian HEIs in first delivery of Green Finance microcredential
5
Modules
24
Staff Trained
6
Asian HEIs
15
Months
GREEN FINANCE | WP3 Kick-off

## Slide 4
Slide 4 of 10
WP3 Timeline
August 2026 - September 2027 (M8-M22)
Three Tasks Structure
T3.1
Preparation Phase
M8-M10 (Aug-Oct 2026)
3 months
T3.2
Training Implementation
M11-M16 (Nov 2026-Apr 2027)
6 months
T3.3
Curriculum Delivery
M17-M22 (May-Sep 2027)
5 months
Key Milestones
M10: Training materials package complete (D3.1)
M13: First training session complete
M16: Second training session + reports (D3.2)
M22: Pilot curriculum delivered at all 6 Asian HEIs (D3.3)
GREEN FINANCE | WP3 Kick-off

## Slide 5
Slide 5 of 10
Three Tasks Overview
T3.1, T3.2, T3.3 Detailed
T3.1: Preparation Phase
- Develop training materials
- Create module templates
- Prepare case studies
- Design assessments
- Build resource library
T3.2: Training
- 2x 1-week intensive
- 24 Asian staff trained
- Hands-on workshops
- Curriculum co-creation
- Teaching practice
T3.3: Curriculum Delivery
- Pilot at 6 Asian HEIs
- 3 EU missions support
- Real student cohorts
- Feedback collection
- Refinement cycle
->
->
Deliverables
D3.1: Training Materials Package
Due: M10
D3.2: Training Reports
Due: M16
D3.3: Pilot Curriculum
Due: M22
GREEN FINANCE | WP3 Kick-off

## Slide 6
Slide 6 of 10
Twinning Model
EU-Asian Partnership for Capacity Building
Three-Stage Development Process
1
EU Preparation
EU partners develop initial materials
|
2
Joint Development
EU-Asian co-creation during training
|
3
Asian-Led Delivery
Asian partners deliver with EU support
Why Twinning Works
- Knowledge transfer embedded in practice, not just theory
- Asian partners own the curriculum from joint development onward
- EU support continues through delivery phase
- Sustainable capacity remains after project ends
GREEN FINANCE | WP3 Kick-off

## Slide 7
Slide 7 of 10
Development Process
From Preparation to Delivery
T3.1: Prepare
Templates
Materials
Case studies
T3.2: Train
Workshops
Co-creation
Practice
T3.3: Deliver
Pilot courses
EU missions
Refinement
->
->
Key Principle: Each stage builds on the previous. Asian partners progressively take ownership, ensuring sustainable capacity beyond the project.
GREEN FINANCE | WP3 Kick-off

## Slide 8
Slide 8 of 10
Partner Roles
EU and Asian Partner Responsibilities
EU Partners (5 institutions)
UT
University of Twente
WP3 Lead, Team 1 Lead
LBUS
Lucian Blaga Univ.
Team 1, Modules 1-3
UNISI
Univ. of Siena
Team 1, Modules 1-3
OU
Open University UK
Team 2 Lead
IHF
Inst. Hautes Finances
Team 2, Modules 4-5
Asian Partners (6 institutions)
BAV
Banking Academy
Vietnam
BUH
Banking Univ. HCMC
Vietnam
PU
Payap University
Thailand
WU
Walailak University
Thailand
WVSU
West Visayas State
Philippines
ADMU
Ateneo de Manila
Philippines
Responsibilities
EU Partners:
- Lead material development
- Deliver training sessions
- Provide ongoing support
- Conduct EU missions
Asian Partners:
- Participate in training
- Co-create materials
- Adapt for local context
- Deliver pilot courses
- Recruit student cohorts
GREEN FINANCE | WP3 Kick-off

## Slide 9
Slide 9 of 10
WP3 Deliverables
D3.1, D3.2, D3.3
D3.1
Training Materials Package
Due: M10 (Oct 2026)
- 5-module curriculum content
- Slide decks and teaching notes
- Case studies (Southeast Asian context)
- Assessment instruments
- Reading lists and resources
D3.2
Training Reports
Due: M16 (Apr 2027)
- Training session documentation
- Participant feedback analysis
- Skills assessment results
- Recommendations for delivery
D3.3
Pilot Curriculum
Due: M22 (Sep 2027)
- Finalized course materials
- Delivery guidelines
- Student feedback synthesis
- Sustainability recommendations
Note: All deliverables are iteratively developed. D3.1 provides the foundation, D3.2 captures training outcomes, and D3.3 represents the refined, pilot-tested curriculum.
GREEN FINANCE | WP3 Kick-off

## Slide 10
Slide 10 of 10
Discussion Questions
Key Topics for Partner Input
1
How can we best leverage the expertise across both tandem teams?
Consider: module assignments, cross-team collaboration, resource sharing
2
What are the specific needs of each Asian partner context?
Consider: local regulations, student profiles, industry connections
3
How do we ensure quality while allowing for local adaptation?
Consider: QA framework, review processes, acceptable variations
4
What are the critical success factors for the pilot delivery?
Consider: student recruitment, faculty readiness, support mechanisms
Next: Session 2 will detail the Tandem Teams structure and module assignments. Please think about your team's specific contributions and questions.
GREEN FINANCE | WP3 Kick-off