## Slide 1
Erasmus+ Capacity Building in Higher Education
T3.1: Preparation Phase
Session 4
WP3 Kick-off Meeting
GREEN FINANCE Project
August 2026 | Virtual Meeting

## Slide 2
Slide 2 of 8
T3.1 Objectives
M8-M10: August-October 2026
Primary Objectives
Develop comprehensive teaching materials for all 5 modules
Establish quality standards and templates for T3.2
Prepare resource library for training sessions
Success Criteria
All templates completed and EU-partners approved
At least 3 case studies developed per module
Assessment instruments ready for pilot testing
D3.1 delivered on time (October 31, 2026)
Timeline
Aug 1-7
Kick-off meeting & planning
Aug 8-28
Sprint 1 (Modules 1 & 4)
Aug 29-Sep 18
Sprint 2 (Modules 2 & 5)
Sep 19-Oct 9
Sprint 3 (Module 3 & polish)
Oct 10-31
Final review & D3.1 submission
D3.1 Due: October 31, 2026
GREEN FINANCE | WP3 Kick-off

## Slide 3
Slide 3 of 8
Material Development Workflow
4-Step Process for Each Module
1
Module Planning
Define learning outcomes, topics, assessment
2
Content Creation
Slides, case studies, readings, exercises
3
Review & Revision
Team review, quality check, refinement
4
Finalization
Format, test, integrate into package
Effort Estimate
Estimated effort: 3-4 person-weeks per module (including all review cycles)
GREEN FINANCE | WP3 Kick-off

## Slide 4
Slide 4 of 8
Templates Overview
Standard Templates for All Modules
Six Standard Templates
Module Outline
Learning outcomes, topics, schedule
Word
Slide Deck
Beamer template with UT branding
LaTeX
Case Study
Real-world application template
Word/PDF
Assessment
Quiz, assignment, rubric templates
Word
Facilitator Guide
Teaching notes, activities, timing
Word
Reading List
Annotated bibliography
Word
Template Features
Consistent structure across all modules
Built-in quality checkpoints
Adaptable for local contexts
Ready for translation (if needed)
GREEN FINANCE | WP3 Kick-off

## Slide 5
Slide 5 of 8
3-Week Sprint Structure
Rapid Development Cycles
Week 1: Create
- Draft module content
- Develop case studies
- Design assessments
Week 2: Review
- Team review
- Tandem partner feedback
- External review (if needed)
Week 3: Revise
- Incorporate feedback
- Finalize materials
- Prepare for next sprint
Sprint Review Dates
Sprint 1
August 28
Modules 1 & 4
Sprint 2
September 18
Modules 2 & 5
Sprint 3
October 9
Module 3 & full package
GREEN FINANCE | WP3 Kick-off

## Slide 6
Slide 6 of 8
Sprint Module Assignments
Who Does What When
Sprint 1 (Aug 8-28)
M1: Foundations
Lead: UT + LBUS
M4: Green Instruments
Lead: OU + IHF
Sprint 2 (Aug 29-Sep 18)
M2: ESG Integration
Lead: UNISI + LBUS
M5: Policy Frameworks
Lead: OU + IHF
Sprint 3 (Sep 19-Oct 9)
M3: Climate Risk
Lead: UT + UNISI
Polish all modules
Lead: All partners
Note: All partners review all modules. Leads are responsible for coordination and final integration.
GREEN FINANCE | WP3 Kick-off

## Slide 7
Slide 7 of 8
T3.1 Milestone Calendar
Key Dates August-October 2026
Critical Milestones
Aug 1-7
Kick-off Meeting
WP3 overview, team formation
Aug 28
Sprint 1 Review
M1 & M4 first drafts complete
Sep 18
Sprint 2 Review
M2 & M5 first drafts complete
Oct 9
Sprint 3 Review
M3 complete, all modules polished
Oct 10-31
Final Review Period
D3.1 finalization
Oct 31
D3.1 Submission
Training Materials Package delivered
Critical Path
Sprint reviews are hard deadlines - delays cascade to D3.1 delivery
GREEN FINANCE | WP3 Kick-off

## Slide 8
Slide 8 of 8
Risk Mitigation for T3.1
Anticipating and Addressing Challenges
Key Risks & Mitigation Strategies
Capacity Constraints
Partners overcommitted
Buffer time in sprints, shared workload
Review Delays
Feedback cycles extend
Fixed review deadlines, pre-scheduled meetings
Quality Issues
Materials below standard
Templates with checkpoints, peer review
Coordination Gaps
Communication breakdowns
Weekly check-ins, shared repository
Scope Creep
Materials become too complex
Learning outcomes as boundaries, simplicity priority
Escalation Path
Issue → Team Lead → Tandem Coordinator → WP3 Lead (UT) → Steering Committee
GREEN FINANCE | WP3 Kick-off